## ขอเป็นตารางอ่านง่ายๆ
Week | Main Tasks & Activities | Key Outcome / What I Learned | Challenge
Week 5 | Initiated the development of the dashboard UI using Node-RED and HTML to monitor production line data based on the approved concept design. | Learned user-friendly interface design principles and practiced integrating HTML/CSS with Node-RED for customized data visualization. | Designing a UI layout that displays all necessary real-time data clearly without making the screen cluttered or complicated for operators.
Week 6 | Configured and established data communication protocols to extract real-time data from production line machines into the Node-RED system. | Gained a solid understanding of industrial data communication systems and basic data logging practices in a manufacturing environment. | Troubleshooting occasional connection drops between the machines and the system, and ensuring the accuracy of the fetched data.
Week 7 | Deployed the Node-RED dashboard for a trial run on the actual production line floor and gathered feedback from the TE team and operators. | Understood the practical needs of frontline users and learned how to optimize the system based on actual factory conditions. | Identifying and fixing unexpected bugs and system lags that only occurred during the live on-site testing.
Week 8 | Finalized the software project, optimized system performance, and created the user manual and technical documentation for the TE ENG department. | Successfully completed the software prototype and enhanced technical documentation skills required for official project handovers. | Balancing time to clear the final bugs while ensuring the user manual is comprehensive and easy to follow before the deadline.